## GANTT
Month
Work packages and tasks |  | WP leader | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
|  |  | 2016 | [9 empty] | 2017 | [11 empty] | 2018 | [11 empty] | 2019
|  | Date | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02
WP1 | Setting up and operating regional FabSpace services | TerraNIS
T1.1 | Hardware installation
T1.2 | Software installation
T1.3 | Data management |  | Month 6: D1.1; Month 8: D1.2, M3
T1.4 | FabSpace staff training
T1.5 | Daily technical support brought by FabSpace staff
Milestones |  |  | Month 4: M1; Month 6: M2; Month 8: M3,4; Month 9: M5
WP2 | Enhancing human capital among the targeted groups of users | ICCS
T2.1 | Work plans for FabSpace integration in any relevant current programme or activity |  | Month 7: D2.1
T2.2 | Entrepreneurship-oriented pilotprogram for students |  | Month 17: D2.3; Month 29: D2.4
T2.3 | Designing new training programmes on innovation leadership knowledge for researchers' life-long learning
T2.4 | Online support for FabSpace users |  | Month 10: D2.2
Milestones |  |  | Month 5: M6; Month 10: M7; Month 17: M8,9; Month 29: M10,11
WP3 | Animation & networking for innovation and entrepreneurial discovery | Corallia | bar: Month 8 to Month 36
T3.1 | Daily FabSpace animation |  | Month 12: D3.1; Month 34: D3.6
T3.2 | Space Science Shops |  | Month 18: D3.2; Month 24: D3.4; Month 34: D3.8
T3.3 | Organisation of local contests |  | Month 18: D3.2; Month 24: D3.4; Month 34: D3.8
T3.4 | Organisation of European contests |  | Month 18: D3.2; Month 24: D3.4; Month 34: D3.8
T3.5 | Bootcamp |  | Month 22: D3.3; Month 28: D3.5; Month 34: D3.7
Milestones |  |  | Month 15: M12; Month 17: M13; Month 21: M14-16; Month 23: M17; Month 27: M18,19; Month 29: M20; Month 33: M21,22
WP4 | Exploitation and dissemination | UoRT | bar: Month 8 to Month 36
T4.1 | Exploitation and dissemination plan |  | Month 8: D4.1; Month 20: D4.2
T4.2 | Study the impact and solutions to the potentially conficting cultures of the partners involved |  | Month 31: D4.3
T4.3 | Sustainability & business plan |  | Month 33: D4.4
T4.4 | Setting up new MSCAs/Erasmus+ actions to sustain the FabSpace Network
T4.5 | Call for expression of interest for new FabSpace services in Europe (12,500€ grants, 7 awarded new partners)
T4.6 | Launch of a worlwide FabSpace network
Milestones |  |  | Month 13: M23; Month 20: M24; Month 30: M25; Month 33: M26; Month 35: M28; Month 36: M27
WP5 | COMMUNICATION | EBN
T5.1 | Communication strategy and implementation |  | Month 12: D5.1
T5.2 | Communication materials |  | Month 12: D5.1; Month 24: D5.2
T5.3 | Organising Geomatics events
Milestones |  |  | Month 3: M29; Month 4: M30; Month 12: M31; Month 24: M32; Month 36: M33
WP6 | Management | UPS
T6.1 | Consortium and project management |  | Month 1: D6.1; Month 36: D6.4
T6.2 | Management of the European Funding
T6.3 | Gender Equality Plan
T6.4 | Meeting organisation
T6.5 | Interface with the European Commission |  | Month 12: D6.2; Month 24: D6.3; Month 36: D6.5
Milestones |  |  | Month 1: M34; Month 8: M35; Month 12: M36; Month 17: M37; Month 24: M38; Month 26: M39; Month 36: M40